## Sheet1
Sr No. | Task Title
1 | Requirement Gathering | Independent
2 | UI UX Design |  | 1
3 | Database Design |  | 1
4 | Backend Api Writing |  |  | 3
5 | Web Application Development |  |  | 1 | 3 | 9
6 | Mobile Application Development |  |  | 1 | 3 | 9
7 | Detecting a Face from a Photo |  |  | 1
8 | Template Formulation |  |  | 2
9 | Template Matching |  |  |  | 7
10 | Testing | [5 empty] | 5 | 6
11 | Error Fixing | [7 empty] | 10
12 | Documentation | [6 empty] | 5 | 6 | 11