## Sheet1
Sr # | Task Title | Time Period In Hours |  |  |  | Task Description | Task Performers
|  | Optimistic | Most Likely | Pessimistic | Resultant
1 | Requirement Gathering | 7 | 12 | 15 | 11.6667 | Gather all the requirements | ALL
2 | UI UX Design | 18 | 27 | 40 | 27.6667 | Design mobile and web screens of system | Mehdi
3 | Database Design | 2 | 5 | 7 | 4.8333 | Design the database schema for the system with some test data | Tahir
4 | Backend Api Writing | 7 | 12 | 17 | 12 | Design the REST API which will bring and post all the data | Tahir
5 | Web Application Development | 27 | 35 | 50 | 36.1667 | Design a web app for admin and teachers for performing the task | Ammar
6 | Mobile Application Development | 20 | 26 | 32 | 26 | Design a mobile app for regular user for performing the task | Raza
7 | Detecting a Face from a Photo | 5 | 12 | 20 | 12.1667 | Detect a face from a image provided | Ammar
8 | Template Formulation | 12 | 22 | 30 | 21.6667 | Template will be formed for each user that will take all images input and sketch a figure that will laterly matched with image. | Mehdi and Raza
9 | Template Matching | 7 | 12 | 18 | 12.1667 | Match a given image with all the template and predict the person | Tahir
10 | Testing | 7 | 10 | 15 | 10.3333 | Test the whole system regriously to detect some errors in system | ALL
11 | Error Fixing | 7 | 10 | 15 | 10.3333 | If some errors are detected then fix them and test them again | Respective Member
12 | Documentation | 7 | 10 | 15 | 10.3333 | Writing a complete user guide for all the users and demonstrating whole process through a video tutorial | Raza and Tahir --- User Guide Mehdi and Ammar --- Video
| Completion | 126 | 193 | 274 | 195.3333